| 2015-16 Business Plan and Budget Timelines |  |  |  |
| --- | --- | --- | --- |
| ### Retreats / Meetings / Events | ### Due Date | ### Budget Tasks | ### Status |
| PC Strategic & Business Planning Retreat | April 9 2014 | Planning for 2015/16 Business Plan & Budget Development |  |
| CLC Strategic & Business Planning Retreat | May 1-2 2014 | 2015/16 Business Plan Development & Feedback on Budget Process |  |
| PC Strategic & Business Planning Retreat | May 21 2014 | - Follow-up to CLC May Retreat – review 2015/16 Business Plan draft - Q4 2013/14 Business Plan Report for June BOG |  |
| PC Meeting | May 21 2014 | Q4 2013/14 Business Plan Update reviewed for June BOG (Q4 2013/14 Financial Projection will be emailed to PC the week of May 26th and will be presented at June BOG) |  |
| CBC Meeting | May 30 2014 | - Develop Initial Pro-Forma assumptions for 2015/16 - Enrollment Projections - Determine process to receive and assess requests for new full-time complement positions - Determine process to receive and assess requests for Strategic Investment Priority Funding |  |
| CBC Meeting | June 13 2014 | - Initiate process to identify budget solutions for 2015/16 (while considering implementation of RCM model) |  |
| PC Meeting | June 17 2014 | PC Approval of Budget Directions and Draft Business Plan (2015-16) |  |
| CBC Meeting | June 27 2014 | - Identify estimated financial capacity in 2015/16 for new full-time complement positions - Receive 2015/16 Budget Directions from PC - Receive Draft 2015/16 Pro-Forma prepared by Finance and Administrative Services Review and distribute |  |
| Finance Department | June | - Request to ITS for BUS Q2 and Budget prep |  |
| Communique to CLC and Budget Administrators/Officers | July 10 2014 | Send 2015/16 Budget Process |  |
| PC Retreat | August TBD | PC prep for September Board Retreat |  |
| CBC Meeting | August 22 2014 | - Review Q1 2014/15 Financial Projections and recommend presentation to PC - 2015/16 Pro-Forma update |  |
| Communique to CBC | August 25 2014 | Send update on the recommendations being sent to PC by CBC |  |
| PC Meeting | September 3 2014 | 2014/15 - Q1 2014/15 Business Plan reviewed for October BOG - 1st Quarter Financial Report 2014/15 received for information (not required to be presented to BOG) |  |
|  |  | 2015/16 - 2015/16 Pro-Forma update |  |
| Communique to CBC | September 15 2014 | Send update on the recommendations being sent to PC for the September 17 PC meeting |  |
| PC Meeting | September 17 2014 | CBC Update to PC: - 2015/16 Pro-Forma and projected deficit - Status of identifying 2015/16 budget solutions (while considering implementation of RCM model) - Discuss processes to receive and assess requests for new Full-Time Complement positions, I/O positions and SIP requests |  |
| CBC Meeting | September 18 2014 | 2015/16 - Ancillary Activity Pro-Forma - Budget Principles from PC |  |
| Communique to CBC | September 18 2014 | Send update on any relevant PC decisions |  |
| BOG Strategic Planning Retreat | September 21-22 2014 | ICDP Scenario Planning |  |
| Communique to CLC and Budget Administrators/Officers | September 25 2014 | Send reminder for: - October 10th Deadline for Submission of requests for 2015-16 New Full-Time Complement and I/O Positions - REVISED DATE: October 20th Deadline for Submission of 2015-16 requests for Strategic Investment Priorities Funding (SIP) - Explain the new processes surrounding submission of requests and assessment of SIP requests - October 15th Deadline for Submission of 2015-16 CSEP Requests |  |
| CBC Meeting | October 3 2014 | 2015/16 - College Contract Activity Pro-Forma - International Education Centre Pro-Forma - Review of Schedule of Rates for Internal Services 2015/16 | Moved to Oct. 17 Moved to Oct. 27 Moved to Oct.27 |
| Communique to CBC | October 6 2014 | Budget Solutions and Budget Pressures template (Due date October 15, 2014) |  |
| CLC and Budget Administrators/Officers | October 9 2014 | 2014/15 - BUS opens for Q2 (OPENED October 14, 2015) |  |
| PC/CBC Members | October 10 2014 | - Deadline for Submission of requests for New Full-Time Complement and I/O Positions |  |
| Communique to CLC and Budget Administrators/Officers | October 15 2014 | Due date for Submission of 2015-16 CSEP Requests |  |
| CBC Members | October 15 2014 | Due date for submitting Budget Solutions and Budget Pressures |  |
| CBC Meeting | October 17 2014 | 2014/15 - Q2 SIP Report presented to CBC | Completed Oct. 3 |
|  |  | 2015/16 - Review updated 2015/16 Pro-Forma & Budget Solutions - Review of Requests for New Full-Time Complement - Review of Requests for I/O Positions and develop recommendations to PC - Identify capacity in 2015/16 to fund Strategic Investment Priorities | Moved to Oct. 27 Moved to Oct. 30 |
| CLC and Budget Administrators/Officers | October 20 2014 | 2014/15 - BUS closed for Q2 (EXTENDED to October 22 due to Delay) |  |
| PC/CBC Members | REVISED DATE October 20 2014 | - Deadline for Submission of requests for requests for Strategic Investment Priorities Funding (SIP) |  |
| Communique to CBC | October 20 2014 | Send update on the materials/ recommendations being sent to PC for the October 22 PC meeting |  |
| CBC/CSIC/CTC | October 21 – November 20 2014 | - Review and assessment of requests for SIP Funding |  |
| PC Meeting | October 22 2014 | 2014/15 - Q2 SIP Report presented to President’s Council |  |
|  |  | 2015/16 CBC to present: - Requests for New Full-Time Complement for approval - Request for I/O Positions for review and approval - Schedule of Rates for Internal Services 2015/16 for review and approval | Deferred to Nov. 2-3 Moved to Oct. 29 |
| CLC Strategic & Business Planning Retreat | October 23 2014 | - Finalization of 2015/16 Business Plan measures and targets |  |
| EXTRA CBC Meeting | October 27 2014 | - Review of 2015/16 Requests for I/O Positions and develop recommendations to PC - Review of Schedule of Rates for Internal Services 2015/16 - Budget solutions & Budget Pressures (Final Review) | Moved from Oct. 17 Moved from Oct. 3 |
| PC Meeting | October 29 2014 | 2014/15 - Q2 SIP Report presented to President's Council - Review Requests I/O Positions (excluding SIP Funded Temp Positions) - Schedule of Rates for Internal Services 2015/16 for review and approval - Review proposed Budget solutions & Budget Pressures | Moved to Oct. 22 Moved from Oct. 22 Moved from Nov. 5 |
| CBC Meeting | October 30 2014 | - Identify capacity in 2015/16 to fund Strategic Investment Priorities - Review SIP Requests - Budget Solutions and Budget Pressures - Update from PC - Budget Solutions and Budget Pressures - Schedule of Rates for Internal Services 2015/16 - Requests for I/O Positions - Balanced Pro-Forma - New Full-Time Complement | Moved from Oct. 17 PC deferred to Nov. 2-3 |
| PC Meeting | November 5 2014 | - 2015/16 Budget Assumptions & Pro-Forma Update - Review proposed Budget Solutions & Budget Pressures - Review Requests I/O Positions (excluding SIP Funded Temp Positions) | Moved to Oct. 29 |
| Communique to CLC and Budget Administrators/Officers | November 6 2014 | Send update on any relevant PC decisions |  |
| CBC Meeting | November 6 2014 | Begin review of SIP requests: - Equipment Requests - Program Development Requests - Business Plan Initiatives (excluding CTC and CSIC requests) - I/O and other temporary positions funded from SIP |  |
| Communique to CLC and Budget Administrators/Officers | November 12 2014 | Send: - Notification of Budget targets - BUS Opening on November 12 |  |
| CLC and Budget Administrators/Officers | November 12 2014 | 2015/16 - BUS opens |  |
| Communique to CLC and Budget Administrators/Officers | November 17 2014 | Notification Memo: Q3 SIP Review Process (Forecast due by December 4, 2014) |  |
| PC Meeting | November 19 2014 | 2014/15 - Q2 2014/15 Business Plan & Financial Projections reviewed for December BOG - 2nd Quarter Financial Report 2014/15 and contingency report |  |
|  |  | 2015/16 - 2015/16 Budget Assumptions and Pro-Forma Update |  |
| CBC Meeting | November 20 2014 | 2014/15 - 2nd Quarter Financial Report 2014/15 and contingency report |  |
|  |  | 2015/16 Continue review of SIP requests: - Equipment Requests - Program Development Requests - Review and approve CSEP requests - Business Plan Initiatives (excluding CTC and CSIC requests) - I/O and other temporary positions funded from SIP - Review of CSIC, CTC, & SEMC SIP Requests | Move to Dec. 1 2014 |
| Communique to CLC and Budget Administrators/Officers | November 24 2014 | Send update on any relevant PC decisions | NA |
| EXTRA CBC Meeting | December 1 2014 | 2015/16 Continue review of SIP requests: - Equipment Requests - Program Development Requests - Technology requests from CTC - Space and infrastructure requests from CSIC - Review and approve CSEP requests | Deferred |
| *Special PC Meeting | December 2 2014 | Review Strategic Investment Projects (SIP) Requests (1 of 4 meetings) - Equipment Requests - Program Development Requests |  |
| PC Meeting | December 3 2014 | Review and approval of SIP requests as recommended by CBC - SIP Requests from College Technologies Committee |  |
| Communique to CLC and Budget Administrators/Officers | December 4 2014 | Send update on any relevant PC decisions | NA |
| CBC Meeting | December 4 2014 | Review Strategic Investment Projects (SIP) |  |
| Communique to CLC and Budget Administrators/Officers | December 5 2014 | Send notification BUS closes on December 9 |  |
| BOG Meeting | December 8 2014 | 2014/15 - 2014/15 Q2 Business Plan & Financial Projections |  |
|  |  | 2015/16 - 2015/16 Budget assumptions and Pro-Forma Report |  |
| CLC and Budget Administrators/Officers | December 9, Noon 2014 | 2015/16 - BUS closes |  |
| PC Meeting | December 10 2014 | Review of Strategic Investment Projects (SIP) - College Space and Infrastructure Committee requests from CSIC |  |
| *Special PC Meeting | December 11 2014 | Review Strategic Investment Projects (SIP) Requests (2 of 4 meetings) SIP Requests from College Budget Committee - Equipment Requests - New Program Development - Other Initiatives/Opportunities - SIP Requests from College Technologies Committee |  |
| Communique to CLC and Budget Administrators/Officers | December 15 2014 | 2014/15 Q3 Significant Adjustments due back to Finance |  |
| *Special PC Meeting | December 16 2014 | Review Strategic Investment Projects (SIP) Requests (3 of 4 meetings) - Decisions on SIP Allocations |  |
| PC Meeting | December 17 2014 | Review and approval of Strategic Investment Projects (SIP) – all categories - Decisions on SIP Allocations |  |
| *Special PC Meeting | December 18 2014 | Finalization of SIP Approvals (4 of 4 meetings) |  |
| Communique to CLC and Budget Administrators/Officers | December 18 2014 | Send update on any relevant PC decisions |  |
| Individual VPs | December 9 - 12 2014 | Area Budget review by VPs |  |
| CBC Meeting | December 19 2014 | 2014/15 - Q3 SIP Report presented to CBC |  |
|  |  | 2015/16 - Finalization of SIP Request Approvals |  |
| Finance & Administrative Services and Advancement | January 2015 | Prepare 2015/16 Business Plan and Budget document |  |
| CBC Meeting | January 8 2015 | - PC Approvals – SIP 2014/15 - Q3 SIP Report presented to CBC - 3rd Quarter Financial Report 2014/15 and contingency report presented at CBC |  |
| PC Meeting | January 21 2015 | - Q3 SIP Report presented to President's Council - 3rd Quarter Financial Report 2014/15 and contingency report presented at PC |  |
|  |  | 2015/16 - Present 2015/16 Business Plan and Budget document for approval |  |
| BOG Meeting | REVISED DATE February 2 2015 | 2014/15 - Q3 2014/15 Business Plan and Financial Projections |  |
|  |  | 2015/16 - 2015/16 Business Plan & Budget for approval |  |

Notes:

Additional CBC and PC meetings required in December to finalize SIP approvals.

CTC and CSIC meetings to be added to schedule.