## critical path
Sample Critical Path
Event Name and Date
| Details | Time Required | Start Date | Deadline | Done | Person Responsible | Notes
PLANNING
Planning
Establish event goals and objectives
Determine evaluation process
Review de-brief notes from past event
Identify target audience
Identify VIPs and roles
Identify date
Check College event calendar
Book location(s)
Confirm location(s)
Decide on virtual platform
Decide if the event should be a webinar or meeting
Decide how many people will attend in person
Agenda
Prepare draft agenda
Circulate for approval
Revise agenda as required
Confirm internal participants
Finalize agenda
Brief senior supervisor
Brief VIPs
Budget
Establish budget
Obtain budget codes
Set up budget template
LOGISTICS
Emcee
Identify Emcee
Contact Emcee
Confirm Emcee
Initiate 1st contact meeting with Emcee
First script review with Emcee
2nd script review with Emcee
Provide Emcee with event information, script and PPT
Host
Identify host
Contact Emcee
Confirm Emcee
Initiate 1st contact meeting with Emcee
First script review with Emcee
2nd script review with Emcee
Provide Emcee with event information, script and PPT
Scripts
Emcee Script
If available, review and update previous Emcee scripts for current event
If not, create new script
Review script
Send draft script to Emcee (once approved)
Finalize script with Emcee feedback
Host Script
If available, review and update previous Host scripts for current event
If not, create new script
Review script
Send draft script to Emcee (once approved)
Finalize script with Hostfeedback
Power Point Presentation
Update any previous event versions and insert new information as required
As needed, prepare new PPT slides from speaking notes/speeches
Collect and merge others' slides as required (i.e. other speakers')
First Review of PPT
Second Review
Review with senior supervisor
Final Review
Food Service
Review available menu options
Plan menu
Estimate quantity needed
Order food/beverages, including linens
Request water jugs/glasses on table
Review food service contract
Finalize confirmation( 48 hrs.)
Gifts
Order thank you gifts for Emcees and others as necessary
Registration/ Greeters
Create links and registration for online attendence
If needed, have individuals posted at major entrances to welcome and register attendees
Parking
Organize parking arrangements
Confirm arrangements
Communicate parking arrangements to appropriate parties
Security
Inform security of event
Provide head of security with a copy of Agenda
AV
Communicate to AV staff
Pre- book internal resources/Equip/Staff
ITS
Communicate to ITS staff
Pre- book internal resources/Equip/Staff
Photographer
Book photographer
Confirm Photographer
Event Materials/Podium
Reserve materials online
Confirm materials are available
Make arrangements for pick up and return
Staging
Book staging
Organize delivery and return
Volunteers
Identify requirements/tasks
Make a volunteer schedule
Put out a call for volunteers
Confirm volunteers
Communicate event information and volunteer responsibilities
Signage
Identify requirements
See what is available and reserve
Order new signage
Order directional signage from Publishing Centre
Reserve directional signage holders
Post directional signage
Flowers
Confirm requirements
Order flowers
Set Up
Establish floor plan
Confirm available set up time
Email Physical Resources with set up instructions and timeline
Deliver small items to location supervisor
Install promotional signage
Inform Physical Resources
Order additional cleaning
Confirm floor plan with location supervisor
Pre- Event Run- thru + Dry run
Sound check
Run thru with key-note speaker
Run thru with Emcee
Sight tour to confirm final details
Additional chairs are pre-booked and available
Reserve Sign for Designated Tables
Check props (i.e. scissors or pens if being used formally)
Test slides and music
Breakdown
Inform Physical Resources
Return All borrowed Materials
Remove all promotional signage
Return all Dept. signage to storage
Follow up on Meal Count
Follow thru on service Issues
Create link to key-note speaker's Speech
Evaluation
Identify evaluation methods
Set-up necessary tools
Focus group
Debrief
Schedule debrief meeting
Prepare notes from debrief
Submit debrief minutes to supervisor
COMMUNICATIONS
Communication Plan
Establish communication objectives
Identify tools required
Invitations
Personal Invitations
Draft hard copy and electronic invitation copy
Review invitation copy
If needed, work with a designer to create any needed graphics
Confirm guest list and appropriate invitation distribution method
Print hard copies if needed
Distribute invitations
Event Brite
Create an EventBrite site promoting your event
Send invitations electronically, and use site to capture registration numbers
Campus Promotion
Signage/Electronic Boards
Book the appropriate signage/boards
Prepare copy
Get copy approved
Posters
Book sign
Prepare copy
Get copy approved
Internal marketing
Submit event on College Events Calendar
Send email asking to post message day of event
Promotion
Contact Marketing Office
Contact Public Relations
Submit to myAC
Info Algonquin
Advise Info Algonquin of event
Thank You
Send out thank you emails to participants, volunteers, guest speakers, and others who helped during the event process
Survey
If needed, create a survey to send out with your thank you message. Use Fluid Surveys or Survey Monkey.
Distribute survey
Collect and aggregate results