## Slide 1
Incredible Journey – Part 2:
Algonquin’s Transition to
Responsibility Center Management

## Slide 2: Incredible Journey – Today’s Presentation
Background
Stakeholder engagement
Allocations – why and how
Impact to Date
Next Steps

## Slide 3: background

## Slide 4: About Algonquin College
  Delivers 272 postsecondary programs plus a roster of apprenticeship, career and college preparation, continuing education, and corporate training programs
  Operates with an annual budget of $320 million
  Serves more than 21,000 fulltime and 43,000 part-time course registrants, including over 1,300 international
  Employs over 4,700 full- and part-time faculty and staff
  10 Academic departments and 21 Non-academic Departments, including Ancillary and International
  Operates on 3 campuses in Ontario (Woodroffe, Pembroke & Perth) as well as internationally

## Slide 5: “Made at Algonquin” approach
Define Audiences
Decide on Fundamentals
Allocation Methodology
Measurement
Timelines

## Slide 6: RCM and Algonquin
  RCM is just a tool – one promoting transparency and accountability
  We were looking to change the “norm” and share responsibility for fiscal sustainability
  We did internal & external feasibility studies and examined the risks
  Had wide internal stakeholder participation
  Built internal principles of Fair, Transparent and Data informed decision making
  Have a robust, cross-college leadership team
  Took small, informed steps and kept exploring options and communicating

## Slide 7: Timelines
Feasibility studies - 2013
Project for “made in Algonquin” model 2014-15
Stakeholder engagement - 2014-2015
First year effective April 1, 2015
Budgeted using RCM principles for FY 2016-17
First Customer Survey against SLA’s Fall 2016
Currently planning for Budget FY 2017-18 in full RCM model
Implementing formal budget feedback process

## Slide 8: Stakeholder Engagement

## Slide 9: Fostering Stakeholder Support
  Strong, visible Leadership
  Pan-department representation
  Gap analysis and Risk Framework
  Town Hall presentations
  “About RCM” sessions
  Internal training focus, including soft skills ‘toolkit’ under development
  Department by department “road show”
  Key audience groups
  Communication is key

## Slide 10: Principles

## Slide 11: RCM Operating Principles
The College operates under provincial regulations & laws.
RCM will be fair, transparent and data informed.
Common institutional practices will prevail
Common purpose & core values are KEY
College wide projects must still go forward and be supported.
College strives for 70/30 split in academic to non-academic expenses
All Departments use the central or corporate administration functions

## Slide 12: Accountability goals in RCM project charter:
Assign financial responsibility to decision makers
Enhance authority of the Dean/Director level
Provide incentives for effective resource management & cost control
Create a budgetary structure that ties resources to performance
Improve budget forecasting and planning
Bring together responsibility, authority and accountability at the Dean/Director level
Decentralized decision making

## Slide 13: Accountability Framework
Accountability Framework must reflect what a Dean or Director is accountable for
  We chose Contribution Margin
Surpluses achieved are shared with the Department to incent budget success
Deficits realized will be required to be paid back by Deans and Directors
In both situations, final results will be adjusted to reflect non-controllable expenses

## Slide 14: Allocations

## Slide 15: Key Financial Measurement: Net Contribution Margin
REVENUE
-
EXPENSES
=
NET CONTRIBUTION MARGIN

## Slide 16: Allocation Methodology
Current Allocation model:
  Tuition already allocated
  Specific & Direct Revenue already allocated
  Direct Costs already budgeted
What did we have to allocate to fully implement RCM:
  Portion of the Provincial Grant
  Central Administration Costs
  Space Costs

## Slide 17: Grant Allocation Method
Grant allocation assigned to Schools based on Weighted Funding Units derived from budgeted enrolment
90% of Provincial grant allocated
Balance allocated to fund tuition hold back, subvention, fund new opportunities, Strategic Investment Priorities (SIP), capital and contingencies
Subvention only promised for 2 years as ‘hold harmless’

## Slide 18: Distribution of Central Administrative Costs
    % of total Direct Costs of Academic departments as defined by current practice
    Direct costs are defined as those expenses already budgeted at an academic department
    Central basket of services represents 18 of 21 non-academic departments

## Slide 19: Distribution of Space Costs
    Total Physical Resources net expenditure budget broken down between:
      Overhead
      Main campus operating costs
    Per square foot allocation (assignable space)
      3 calculations
      All departments charged overhead including rural and leased space
      At Main Campus only –
        Operating Costs
        Open Classroom usage %

## Slide 20: Impact to date

## Slide 21: Operationalizing RCM
Steering Committee ended after 2 years in November 2015, mandate largely complete
During first 24 months had dedicated Project Manager
Ownership of budget process, documentation, financial analysis & day to day support for RCM with Finance
College Budget Committee (CBC) assumes Governance role and needs to reinforce the trial aspect of RCM allocations, recommends changes in assumptions, timing & overall targets to Senior Management

## Slide 22: Lessons learned to date:
Devil is in the details
2-year hold harmless period allows process issues to be raised and discussed
We did not fundamentally change accounting or overall budget principles
Level of transparency into financials is perceived differently by each group – generally positive
There is a need for standardization of processes
Support for RCM, training & communications must be on-going
Some Deans/Directors still struggling with concepts and decentralized approach under RCM

## Slide 23: Lessons learned to date:
Challenges on what is “center” to the College budget and what is de-centralized continues to evolve
RCM in the short term is not a BIG impact because we already had many of the RCM principles in place – next year may be a different impact in a full RCM budget cycle
There will be other impacts around RCM in future years
Involvement at all levels is good and was a key success factor - keep up effective communication around RCM
Area target setting was utilized and need to be adjusted to give more time at department level for preparation
An excellent tool to learn about the College and its processes as a whole

## Slide 24: Impact
We’ve changed the status quo – budgets are more of a discussion
More conversations on collaboration, alignment and standardization
Still challenged on financial confines of budgeting (shared resources) and “static” budgeting model (annual)
Success in surplus sharing – 22 of 31 departments in FY 2014-15 kept 25% of net surplus
FY2015-2016 surplus sharing at 40%

## Slide 25: Next Steps

## Slide 26: Future thoughts – beyond Year-1
Space costs
  Further refinement of allocation
  Timeliness of vacating/changing space
Central Administrative cost allocations
  Use of Gross margin or alternative base
  Remove flow-through revenue & costs
  Allowing departments to “opt out” of certain cost categories
Revenue
  % of grant allocation – flat or department specific
  Subvention – use, and total dollar value

## Slide 27
Stay tuned! Further updates next year!
Comments and Questions